| Boreland Action Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Community Benefit Funding |  |  |  |  |
| What could be done | By whom | How it will be achieved | Benefits | When Delivered |
| Simplify administration of windfarm community benefit funding | HCI working with windfarm funders | HCI now promotes the use of community benefit funding from Ewe Hill, Minsca and Crossdykes within the community and runs the village hall. | Simple application form captures details required so HCI can report back to funders on how funds are spent | Simple application form online |
| Seek funding from other sources for other projects where appropriate | HCI working with other funders | HCI will make applications when need/opportunity arises | HCI will seek to fund activity that cannot be funded in whole or part through windfarm funding |  |
| Training and Education |
| What could be done | By whom | How it will be achieved | Benefits | When Delivered |
| Training bursaries | HCI | Community Benefit Funds offer max £1k per person for training from HCI | Individuals helped with costs of education or training events covering full time University and college courses, shorter courses lasting a day or more, practical courses, driving lessons. | Launched 2022/23 |
| Training events | HCI | Community members or HCI organise training providers | Part or full day events for groups of community members |  |
| Environment (walks, environment protection, environmental tourism) |  |  |  |  |
| What could be done | By whom | How it will be achieved | Benefits | When Delivered |
| Extend walks in and around the village | HCI or individual community members | Benefit funding supporting volunteers and contractors. Land owner agreements may be needed including maintenance responsibilities. Better information and signage | Allow longer walks and more certainty about where to walk |  |
| Improve access and amenity at specific sites eg Black Esk Reservoir. Other ideas to be considered | HCI and NMCC perhaps working with Eskdalemuir CC | Agreement possible with Forest and Land Scotland | Site previously a focus for walks and picnics currently lacks signage and facilities |  |
| Rewilding and tree planting | Individual community members/land owners | Agreement with HCI to secure community benefits. Local funds could match other sources | Small areas of new habitat and or trees support nature and carbon benefits |  |
| Promote area for outdoor activities | Individual community members/land owners, relevant third party | Especially linked to opportunities to engage with local nature and landuse . Planned “Nature Connections” working with Southern Uplands Partnership programme to be delivered in 2026 | Improved provision of information online or leaflets for local residents and attracting people to the area | . |
| Key Community Services |  |  |  |  |
| What could be done | By whom | How it will be achieved | Benefits | When Delivered |
| Boreland Village Hall maintenance | HCI/community groups and members | Volunteers time, community benefit funding and booking income used to maintain hall to high standard and available for booking by community | Hall actively used for programme of community clubs and events. | Ongoing Roof repairs completed February 2026 |
| Paid for Community Capacity | HCI/NMCC | Engage a community worker to support administrative tasks like use of the hall and provide momentum for actions in the community | Programme of events expands, projects move forward, volunteers encouraged | Hannah Pearson appointed July 2025 |
| Playpark Outdoor Gym | HCI in agreement with DGC | Progressing idea to reposition new equipment at hall | Activity opportunities extended | Aiming for later 2026 |
| Community Transport facilities | HCI perhaps working with a provider | Funding to support a provider. ACTS provides existing service that might be extended to assist school, hospital or other travel needs | Community members have ready access to transport to services such as hospital, shops etc |  |
| Community Transport facilities | HCI perhaps working with a provider | Funding to provide a dedicated bookable vehicle in the community for community use. Consider EV or e-bikes | Community members have ready access to transport to services such as hospital, shops etc |  |
| Create opportunities for members of the community to meet | HCI working with a caterer and volunteers | Facilitate monthly (lunch) events | Encourages social interaction, connects the community and develops interest in volunteering and community projects | Starting January 2024 Soup and Blether runs monthly with funding support |
| Create opportunities for members of the community to volunteer | HCI working with action sub groups | Maintain programme of social events, and a tidy and attractive village environment. | Community has opportunities to enjoy events through the year. Community has greater provide in its appearance | Bobby Bingo runs monthly plus occasional events programme. |
| Addressing Climate Change |  |  |  |  |
| What could be done | By whom | How it will be achieved | Benefits | When Delivered |
| Reinvestment in renewable schemes | HCI | Use funding to leverage investment in renewable schemes that gave longer term community benefits | Reduce cost in running community facilities. Possible community ownership of larger projects. | Solar panels and battery installed on hall February 2026 |
| Support community members to investigate renewable options | HCI with third parties | While community funds cannot be used to support individuals helping ensure community members know what options are available might help. | Ensure community members have access to available advice and funding for their needs | Changeworks event January 2026 |
| Affordable housing | HCI with third parties | Research opportunities to use available land to build low energy use housing for rent | Provide energy efficient housing stock as example of how to reduce energy costs |  |
| Community Charge point | HCI with third parties | Research the opportunity to provide a charge point in the community | Provide access to charging to encourage use of EVs |  |
| Other ideas |  |  |  |  |
| Small Business premises | HCI with third parties | Consider opportunities to develop low cost start up units for business use within the community. One use perhaps for redundant buildings | Help start up businesses establish in the community |  |
| Community ownership of the school building | HCI with third parties. Community support required throughout | Explore feasibility of community taking ownership of the old school to deliver affordable rentable accommodation. Requires needs analysis, feasibility work, detailed planning, business planning ,CAT, major funding , long term management. | Building in the centre of the village compromising existing facilities. | Needs analysis presented to community March 2026. |

Members refers to all residents within the community area

Priority larger projects

Version updated 29 March 2026